## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Introduction to Project & Requirement Analysis | MUST HAVE | No Dependency | Veena Akkenapalli | 3- Completed
S1 | S1 | US-001 | ETL Workflow Design & Architecture Planning | MUST HAVE | Research Docs | Veena Akkenapalli | 3- Completed
S2 | S2 | US-001 | Environment Setup (Docker + Airflow) | MUST HAVE | Docker docs | Veena Akkenapalli | 3- Completed
S2 | S2 | US-001 | Log Data Generation & Preprocessing | MUST HAVE | Python, Pandas | Veena Akkenapalli | 3- Completed
S2 | S2 | US-001 | ETL Pipeline Implementation (Extract + Transform) | MUST HAVE | Python | Veena Akkenapalli | 3- Completed
S3 | S3 | US-001 | Airflow DAG Implementation & Scheduling | MUST HAVE | Apache Airflow | Veena Akkenapalli | 3- Completed
S3 | S3 | US-001 | PostgreSQL Integration (Load Phase) | MUST HAVE | PostgreSQL | Veena Akkenapalli | 3- Completed
S4 | S4 | US-001 | Anomaly Detection Logic Implementation | SHOULD HAVE | Python Logic | Veena Akkenapalli | 3- Completed
S4 | S4 | US-001 | Streamlit Dashboard & Visualization | SHOULD HAVE | Streamlit,Plotly | Veena Akkenapalli | 3- Completed
S4 | S4 | US-001 | Testing, Optimization & Docker Integration | MUST HAVE | Docker, Debugging | Veena Akkenapalli | 3- Completed
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 69 | 1 | 2 | 3 | 3 | 4 | 5 | 7 | 7 | 7 | 5 | 5 | 5 | 4 | 3
SPRINT 1 BACKLOG
US-001 | 1 | Project Introduction & Requirement Understanding | 2026-02-05 | 2026-02-06 | Varshini Maddula | Others | Completed | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 2 | Designing ETL Workflow & Architecture | 2026-02-07 | 2026-02-09 | Varshini Maddula | Design | Completed | 4 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 3 | Research on Airflow & Docker | 2026-02-10 | 2026-02-12 | Varshini Maddula | Others | Completed | 5 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 4 | Setup Airflow + Docker Environment | 2026-02-13 | 2026-02-15 | Varshini Maddula | Setup | Completed | 6 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
US-001 | 5 | Log Data Generation & Understanding | 2026-02-16 | 2026-02-17 | Varshini Maddula | Coding | Completed | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
US-001 | ..6 | Basic ETL (Extract + Transform) | 2026-02-18 | 2026-02-19 | Varshini Maddula | Coding | Completed | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
US-001 | ..7 | Airflow DAG Implementation & Scheduling | 2026-02-20 | 2026-02-24 | Varshini Maddula | Build | Completed | 10 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
US-001 | ..8 | PostgreSQL Integration & Data Storage | 2026-02-25 | 2026-02-28 | Varshini Maddula | Coding | Completed | 8 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
US-001 | ..9 | Anomaly Detection Logic Implementation | 2026-03-01 | 2026-03-05 | Varshini Maddula | Coding | Completed | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
US-001 | ..10 | Streamlit Dashboard + Visualization + Docker Integration | 2026-03-06 | 2026-03-19 | Varshini Maddula | Integration/Testing | Completed | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 2 | Lack of clarity on ETL pipeline design and workflow structure | Researched ETL architecture and referred documentation to define clear pipeline stages (Extract, Transform, Load)
Sprint 1 | Day 4 | Confusion in setting up Apache Airflow environment | Followed official Airflow documentation and tested setup using Docker containers
Sprint 2 | Day 6 | Issues in generating and structuring log data for processing | Created custom log generator and validated data format using Pandas
Sprint 2 | Day 7 | Difficulty in transforming unstructured logs into structured format | Broke transformation into smaller steps and implemented modular functions
Sprint 3 | Day 9 | Confusion in designing anomaly detection logic | Researched threshold-based detection techniques and implemented rule-based anomaly detection
Sprint 3 | Day 12 | SQL queries taking longer time due to large dataset | Debugged DAG step-by-step and tested individual tasks before integration
Sprint 4 | Day 16 | Errors while configuring Airflow DAG and task dependencies | Optimized queries using indexing and improved database schema design
Sprint 4 | Day 20 | Issues in connecting backend data with Streamlit dashboard | Verified database connections and used efficient queries to fetch data
Sprint 4 | Day 24 | Difficulty in Dockerizing multi-service architecture (Airflow + DB + Dashboard) | Fixed docker-compose configuration and tested services independently before integration

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2026-02-05 | 2026-02-19 | Varshini Maddula | Understanding ETL concepts, setting up project structure, researching Airflow & Docker | Jumping into coding without planning | Reading documentation & planning architecture | Designed initial architecture and finalized tech stack (Airflow, Docker, PostgreSQL, Streamlit)
2 | Sprint 2 | 2026-02-20 | 2026-03-06 | Varshini Maddula | Developing ETL pipeline (data extraction + transformation), generating log datasets | Overcomplicating transformations | Writing modular and clean code | Completed ETL modules and validated structured log data processing
3 | Sprint 3 | 2026-03-07 | 2026-03-21 | Varshini Maddula | Implementing Airflow DAG, integrating PostgreSQL, anomaly detection logic | Delaying testing of DAG workflows | Debugging and improving pipeline efficiency | Successfully orchestrated pipeline using Airflow and stored results in PostgreSQL
4 | Sprint 4 | 2026-03-22 | 2026-04-05 | Varshini Maddula | Building Streamlit dashboard, visualization with Plotly, Dockerizing full system | Ignoring UI/UX improvements initially | Testing, optimization, and polishing | Completed interactive dashboard, containerized project, and finalized deployment-ready system
5
6
7